## User stories (hidden)
User Stories
Groups | ID | As a... | I want/need ... | so that/because... | Additional Information | Story Point Estimation
1. Creating an account and logging in
2. Handling current share portfolio
3. Adding balance and purchasing shares
4. Security
5. Other

## Backlog Overall
ID | Task
1 | Arduino Wifi Module Assemble
2 | Look Into Locks For Application
3 | Research Android Development
4 | Research Python Libraries
5 | Research Arduino Libraries
6 | Pick Suitable Sensors For Project
7 | Research ESP
8 | Aquire Hardware From Workshop
9 | Research And Design Lo-Fi Interface
10 | Research Current In Use Smart Home Systems
11
12
13
14
15
16
17
18
19
20
21
22

## Product BacklogSprint Plan
ID | Item Priority | Item Description | Story Point Estimation | Velocity
1 | High | Arduino Wifi Module Assemble | 10 | 131
2 | High | Look Into Locks For Application | 5 |  | Group Roles
3 | High | Research Android Development | 20 |  | Role | Assigned to
4 | High | Research Python Libraries | 20 |  | Product Owner | Jung-Moo
5 | High | Research Arduino Libraries | 20 |  | Scrum Master | Alex
6 | High | Pick Suitable Sensors For Project | 10 |  | Team member 1 | Igor
7 | High | Research ESP | 30 |  | Team member 2 | Waleed
8 | High | Aquire Hardware From Workshop | 3
9 | High | Research And Design Lo-Fi Interface | 10
10 | High | Research Current In Use Smart Home Systems | 3 |  |  |  | 2 weeks a sprint?
Sprint 1
[5 empty] | Plan |  |  | Rollover From Previous Sprint | Rollover Task Allocation
[5 empty] | Planned (ID) | Status | Task Allocation
[5 empty] | 1 | Ongoing | Jung-Moo | N/A | N/A
[5 empty] | 2 | Ongoing | Alex | N/A | N/A
[5 empty] | 3 | Ongoing | Igor/Waleed | N/A | N/A
[5 empty] | 4 | Ongoing | Igor/Waleed | N/A | N/A
[5 empty] | 5 | Ongoing | Jung-Moo | N/A | N/A
[5 empty] | 6 | Ongoing | Alex/Igor | N/A | N/A
[5 empty] | 7 | Ongoing | Jung-Moo | N/A | N/A
[5 empty] | 8 | Ongoing | Jung-Moo | N/A | N/A
[5 empty] | 9 | Ongoing | Alex/Igor | N/A | N/A
[5 empty] | 10 | Ongoing | Waleed/Alex | N/A | N/A
Goal Of First Sprint
The Goal of the first sprint is to prepare our designs and ensure we have the skills needed to complete the next sprint which will be creating the basic framework of our project.
0
Sprint 2
[5 empty] | Plan |  |  | Rollover From Previous Sprint | Rollover Task Allocation
[5 empty] | Planned (ID) | Status | Task Allocation
Goal Of Second Sprint
0
Goal Of Third Sprint
Sprint 3
[5 empty] | Plan |  |  | Rollover From Previous Sprint | Rollover Task Allocation
Total Story Point Estimation: |  |  | 131 |  | Planned (ID) | Status | Task Allocation
Note - 1 storypoint is equal to 1 hours work.

## Sprint Backlog (Sprint 1)
Sprint Tasks |  |  | Days of the Sprint
Sprint 1 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 17 | 18 | 19
Arduino Wifi Module Assemble | Jung-Moo | 10
Look Into Locks For Application | Alex | 5
Research Android Development | Igor/Waleed | 20
Research Python Libraries | Igor/Waleed | 20
Research Arduino Libraries | Jung-Moo | 20
Pick Suitable Sensors For Project | Alex/Igor | 10
Research ESP | Jung-Moo | 30
Aquire Hardware From Workshop | Jung-Moo | 3
Research And Design Lo-Fi Interface | Alex/Igor | 10
Research Current In Use Smart Home Systems | Waleed/Alex | 3
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.

## Sprint 1 Retrospective
Sprint 1 Retrospective

## Sprint 1 Review
Sprint 1 Review

## Sprint Backlog (Sprint 2)
Sprint Tasks |  |  | Days of the Sprint
Sprint 2 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 17 | 18
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.

## Sprint 2 Retrospective
Sprint 2 Retrospective

## Sprint 2 Review
Sprint 2 Review

## Sprint Backlog (Sprint 3)
Sprint Tasks |  |  | Days of the Sprint
Sprint 3 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 17 | 18 | 19
Gain understanding of the Bootstrap framework | Alex/Igor | 6 | Days of the Sprint 2: 2; Days of the Sprint 4: 2; Days of the Sprint 6: 2
Create a responsive website via CSS | Alex/Igor | 20 | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1
Complete balance transaction in the database | Emilio | 2 | bar: Days of the Sprint 18 to Days of the Sprint 19
Implement balance transaction to settings page | Emilio | 2 | bar: Days of the Sprint 5; Days of the Sprint 19
Move Add funds from settings to a new window via the balance button | Emilio | 3 | Days of the Sprint 6: 3
Move update database buttons from dashboard to settings page for a better UI look | Emilio | 1 | bar: Days of the Sprint 8; Days of the Sprint 19
Export transaction to an excel sheet external | Emilio | 2 | bar: Days of the Sprint 9
Implement algorithm to complete profit/loss graphs | Jung-Mo | 4 | bar: Days of the Sprint 1 to Days of the Sprint 4
Implement Macro to automatically buy and sell at specified prices | Jung-Mo | 10 | bar: Days of the Sprint 8 to Days of the Sprint 11; Days of the Sprint 14 to Days of the Sprint 16; Days of the Sprint 17 to Days of the Sprint 19
Gain understanding on how to implement and create bots to use on the exchange | Jung-Mo | 20 | Days of the Sprint 1: 3; Days of the Sprint 3: 3; Days of the Sprint 5: 3; Days of the Sprint 7: 3; Days of the Sprint 9: 3; Days of the Sprint 11: 3; Days of the Sprint 12: 2
Implement bots using knowledge gathered in research | Jung-Mo | 20 | Days of the Sprint 2: 2; Days of the Sprint 4: 2; Days of the Sprint 6: 2; Days of the Sprint 8: 2; Days of the Sprint 10: 2; Days of the Sprint 12: 2; Days of the Sprint 14: 2; Days of the Sprint 16: 2; Days of the Sprint 18: 2; Days of the Sprint 19: 2
| Total | 90 | 84 | 79 | 73 | 68 | 62 | 55 | 50 | 46 | 39 | 35 | 30 | 25 | 24 | 20 | 18 | 14 | 0 | 0 | 0 | 0 | 0 | 12 | 7 | 0
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.

## Sprint 3 Retrospective
Sprint 3 Retrospective

## Sprint 3 Review
Sprint 3 Review

## FunctionalNonFunctional Requirm (hidden)
Requirements
Functional Requirments | Non-Functional Requirements

## Knowledge acquisition tasks (hidden)
LIST OF KNOWLEDGE ACQUISITION TASKS
Item number | Item Description
1 | How to create a database in order to store all of the necessary details. For example learn SQL and other techniques
2 | Learn API needed to create graphs for website
3
4
5
6
7
8
9
10
11

## References (hidden)
REFERENCES