## Agile Product Backlog
AGILE PRODUCT BACKLOG SMART HOME SYSTEM
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
Sprint 1
1 | Arduino Wifi Module Assembly. | " " | Jung-Mo | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 10 | Yes | This section is for the drop-down list
2 | Research Locks That Can Be Used With Application. | " " | Alex | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 5 | Yes
3 | Research The Abdroid Development Kit Ready For Construction. | " " | Multiple Members | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 20 | Yes | Yes | High | Complete | Alex
4 | Research Python Libararies. | " " | Multiple Members | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 20 | Yes | No | Medium | In Progress | Igor
5 | Research Arduino Libararies. | " " | Jung-Mo | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 20 | Yes |  | Low | Not Started | Jung-Mo
6 | Pick Suitable Sensors For The Project. | " " | Multiple Members | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 10 | Yes |  |  |  | Walid
7 | Research ESP. | " " | Jung-Mo | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 30 | Yes |  |  |  | Multiple Members
8 | Get Needed Hardware From Workshop. | " " | Jung-Mo | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 3 | Yes
9 | Research & Design LO-FI Interface. | " " | Multiple Members | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 10 | Yes
10 | Research Current In Use Smart Home Systems. | " " | Multiple Members | 2020-09-15 | 2020-10-15 | No | Yes | High | Complete | 3 | Yes
Sprint 2
1 | Set Up Web Server. | " " | Jung-Mo | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 30 | Yes
2 | Design Database. | " " | Multiple Members | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 10 | Yes
3 | Research Block Chain Technology. | " " | Jung-Mo | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 15 | Yes
4 | Research Java SQL Libraries. | " " | Jung-Mo | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 5 | Yes
5 | Further Expand Lo-FI Interface. | " " | Alex | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 10 | Yes
6 | Make Test List And Perform Tests. | " " | Multiple Members | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 10 | Yes
7 | Continue Building Pages In Android Studio. | " " | Igor | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 30 | Yes
8 | Research How To Get Arduino To Send & Receive. | " " | Jung-Mo | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 15 | Yes
9 | Research Voice Recognition API. | " " | Alex | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 15 | Yes
10 | Build Thumbnails For Android Application. | " " | Alex | 2020-10-15 | 2020-11-15 | No | Yes | High | Complete | 5 | Yes
Sprint 3
1 | Perform PHP Scripting. | " " | Jung-Mo | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 50 | Yes
2 | Continue Implementation Of Sensors. | " " | Jung-Mo | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 50 | Yes
3 | Develop And Implement SQL Code For Android Application. | " " | Walid | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 10 | Yes
4 | Continue Construction Of Android Pages Ready For Programming. | " " | Multiple Members | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 10 | Yes
5 | Remake Documentation For Agile Project. | " " | Alex | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 10 | Yes
6 | Connect The Database And Populate Said Database. | " " | Igor | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 50 | Yes
7 | Connect Database To Android Part Of Project. | " " | Igor | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 50 | Yes
8 | Continue To Learn The Android Development Kit. | " " | Multiple Members | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 50 | Yes
9 | Create Technical Guide For Engineers Reference. | " " | Jung-Mo | 2020-11-15 | 2020-12-15 | No | Yes | High | In Progress | 2 | Yes
Sprint 4
" "
" "
" "
Sprint 5
" "
" "
" "
Sprint 6
" "
" "
" "