## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | DAY 20 | DAY 21 | DAY 22 | DAY 23 | DAY 24 | DAY 25 | DAY 26 | DAY 27 | DAY 28 | DAY 29 | DAY 30 | SPRINT REVIEW
Sprint #1
Arduino Wifi Module Assembly. | 10 | Jung-Mo | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research Locks That Can Be Used With Application. | 5 | Alex | Complete | 5 | [30 empty] | 5 | bar: DAY 1 to DAY 5
Research The Abdroid Development Kit Ready For Construction. | 20 | Multiple Members | Complete | 20 | [30 empty] | 20 | bar: DAY 1 to DAY 20
Research Python Libararies. | 20 | Multiple Members | Complete | 20 | [30 empty] | 20 | bar: DAY 1 to DAY 20
Research Arduino Libararies. | 20 | Jung-Mo | Complete | 20 | [30 empty] | 20 | bar: DAY 1 to DAY 20
Pick Suitable Sensors For The Project. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research ESP. | 30 | Jung-Mo | Complete | 30 | [30 empty] | 30 | bar: DAY 1 to DAY 30
Get Needed Hardware From Workshop. | 3 | Jung-Mo | Complete | 3 | DAY 1: 3 | 3
Research & Design LO-FI Interface. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research Current In Use Smart Home Systems. | 3 | Multiple Members | Complete | 3 | [30 empty] | 3 | bar: DAY 1 to DAY 3
Sprint #2
Set Up Web Server. | 30 | Jung-Mo | Complete | 30 | [30 empty] | 30 | bar: DAY 1 to DAY 30
Design Database. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research Block Chain Technology. | 15 | Jung-Mo | Complete | 15 | [30 empty] | 15 | bar: DAY 1 to DAY 15
Research Java SQL Libraries. | 5 | Jung-Mo | Complete | 5 | [30 empty] | 5 | bar: DAY 1 to DAY 5
Further Expand Lo-FI Interface. | 10 | Alex | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Make Test List And Perform Tests. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Continue Building Pages In Android Studio. | 30 | Igor | Complete | 30 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 30
Research How To Get Arduino To Send & Receive. | 15 | Jung-Mo | Complete | 15 | [30 empty] | 15 | bar: DAY 1 to DAY 15
Research Voice Recognition API. | 15 | Alex | Complete | 15 | [30 empty] | 15 | bar: DAY 1 to DAY 15
Build Thumbnails For Android Application. | 5 | Alex | Complete | 5 | DAY 1: 1; DAY 2: 2; DAY 3: 1; DAY 4: 1 | 5
Sprint #3
Perform PHP Scripting. | 50 | Jung-Mo | In Progress | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2 | 50
Continue Implementation Of Sensors. | 50 | Jung-Mo | In Progress | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2 | 50
Develop And Implement SQL Code For Android Application. | 10 | Walid | In Progress | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Continue Construction Of Android Pages Ready For Programming. | 10 | Multiple Members | In Progress | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Remake Documentation For Agile Project. | 10 | Alex | In Progress | 10 | DAY 1: 1; DAY 2: 1; DAY 3: 1; DAY 4: 1; DAY 5: 2; DAY 6: 2; DAY 7: 2 | 10
Connect The Database And Populate Said Database. | 50 | Igor | In Progress | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2 | 50
Connect Database To Android Part Of Project. | 50 | Igor | In Progress | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2 | 50
Continue To Learn The Android Development Kit. | 50 | Multiple Members | In Progress | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2 | 50
Create Technical Guide For Engineers Reference. | 2 | Jung-Mo | In Progress | 2 | [30 empty] | 2 | bar: DAY 1 to DAY 2
Sprint #4
Sprint #5
Sprint #6
TOTAL |  |  |  | 558 | 37 | 35 | 33 | 32 | 32 | 30 | 30 | 27 | 27 | 27 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 558