## Agile Sprint Backlog
AGILE SPRINT BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14 | DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | DAY 20 | DAY 21 | DAY 22 | DAY 23 | DAY 24 | DAY 25 | DAY 26 | DAY 27 | DAY 28 | DAY 29 | DAY 30 | SPRINT REVIEW
Sprint #1
Arduino Wifi Module Assembly. | 10 | Jung-Mo | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research Locks That Can Be Used With Application. | 5 | Alex | Complete | 5 | [30 empty] | 5 | bar: DAY 1 to DAY 5
Research The Abdroid Development Kit Ready For Construction. | 20 | Multiple Members | Complete | 20 | [30 empty] | 20 | bar: DAY 1 to DAY 20
Research Python Libararies. | 20 | Multiple Members | Complete | 20 | [30 empty] | 20 | bar: DAY 1 to DAY 20
Research Arduino Libararies. | 20 | Jung-Mo | Complete | 20 | [30 empty] | 20 | bar: DAY 1 to DAY 20
Pick Suitable Sensors For The Project. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research ESP. | 30 | Jung-Mo | Complete | 30 | [30 empty] | 30 | bar: DAY 1 to DAY 30
Get Needed Hardware From Workshop. | 3 | Jung-Mo | Complete | 3 | DAY 1: 3 | 3
Research & Design LO-FI Interface. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research Current In Use Smart Home Systems. | 3 | Multiple Members | Complete | 3 | [30 empty] | 3 | bar: DAY 1 to DAY 3
Sprint #2
Set Up Web Server. | 30 | Jung-Mo | Complete | 30 | [30 empty] | 30 | bar: DAY 1 to DAY 30
Design Database. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Research Block Chain Technology. | 15 | Jung-Mo | Complete | 15 | [30 empty] | 15 | bar: DAY 1 to DAY 15
Research Java SQL Libraries. | 5 | Jung-Mo | Complete | 5 | [30 empty] | 5 | bar: DAY 1 to DAY 5
Further Expand Lo-FI Interface. | 10 | Alex | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Make Test List And Perform Tests. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Continue Building Pages In Android Studio. | 30 | Igor | Complete | 30 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 30
Research How To Get Arduino To Send & Receive. | 15 | Jung-Mo | Complete | 15 | [30 empty] | 15 | bar: DAY 1 to DAY 15
Research Voice Recognition API. | 15 | Alex | Complete | 15 | [30 empty] | 15 | bar: DAY 1 to DAY 15
Build Thumbnails For Android Application. | 5 | Alex | Complete | 5 | DAY 1: 1; DAY 2: 2; DAY 3: 1; DAY 4: 1 | 5
Sprint #3
Perform PHP Scripting. | 50 | Jung-Mo | Complete | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2; DAY 11: 5; DAY 16: 5; DAY 18: 5; DAY 19: 5; DAY 25: 5; DAY 28: 5 | 50
Continue Implementation Of Sensors. | 50 | Jung-Mo | Complete | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2; DAY 12: 5; DAY 13: 5; DAY 14: 5; DAY 15: 5; DAY 17: 5; DAY 20: 5 | 50
Develop And Implement SQL Code For Android Application. | 10 | Walid | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Continue Construction Of Android Pages Ready For Programming. | 10 | Multiple Members | Complete | 10 | [30 empty] | 10 | bar: DAY 1 to DAY 10
Remake Documentation For Agile Project. | 10 | Alex | Complete | 10 | DAY 1: 1; DAY 2: 1; DAY 3: 1; DAY 4: 1; DAY 5: 2; DAY 6: 2; DAY 7: 2 | 10
Connect The Database And Populate Said Database. | 50 | Igor | Complete | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2; DAY 12: 5; DAY 14: 5; DAY 16: 5; DAY 18: 5; DAY 20: 5; DAY 22: 5 | 50
Connect Database To Android Part Of Project. | 50 | Igor | Complete | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2; DAY 11: 5; DAY 13: 5; DAY 15: 5; DAY 17: 5; DAY 19: 5; DAY 21: 5 | 50
Continue To Learn The Android Development Kit. | 50 | Multiple Members | Complete | 50 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2; DAY 11: 5; DAY 13: 5; DAY 15: 5; DAY 17: 5; DAY 19: 5; DAY 21: 5 | 50
Create Technical Guide For Engineers Reference. | 2 | Jung-Mo | Complete | 2 | [30 empty] | 2 | bar: DAY 1 to DAY 2
Sprint #4
Implement Voice Commands & Air Quality Functionality. | 20 | Igor | Complete | 20 | DAY 1: 2; DAY 2: 2; DAY 3: 2; DAY 4: 2; DAY 5: 2; DAY 6: 2; DAY 7: 2; DAY 8: 2; DAY 9: 2; DAY 10: 2; DAY 11: 2; DAY 12: 2; DAY 13: 2; DAY 14: 2; DAY 15: 2 | 20
Weather API Implementation. | 50 | Jung-Mo | Complete | 50 | DAY 1: 5; DAY 2: 5; DAY 3: 5; DAY 4: 5; DAY 5: 5; DAY 6: 5; DAY 7: 5; DAY 8: 5; DAY 9: 5; DAY 29: 5; DAY 30: 5 | 50
Binary File Functionality Algorithm. | 5 | Jung-Mo | Complete | 5 | DAY 1: 2; DAY 3: 2; DAY 5: 1 | 5
Implement Android Pages That Need To Be Implemented. | 20 | Multiple Members | Complete | 20 | [30 empty] | 20 | bar: DAY 1 to DAY 20
Implement Settings Page Functionality. | 10 | Walid | Complete | 10 | DAY 1: 2; DAY 4: 2; DAY 9: 2; DAY 10: 2; DAY 11: 2 | 10
Implement Arduino HTTP Connection. | 30 | Multiple Members | Complete | 30 | DAY 1: 5; DAY 4: 5; DAY 7: 5; DAY 9: 5; DAY 11: 5; DAY 13: 5 | 30
Implement Motion Sensor On Node MCU & Fan Control. | 50 | Jung-Mo | Complete | 50 | DAY 1: 5; DAY 3: 5; DAY 5: 5; DAY 7: 5; DAY 8: 5; DAY 9: 5; DAY 12: 5; DAY 15: 5; DAY 21: 5; DAY 24: 5 | 50
Finalise Poster & Abstract | 15 | Alex | Complete | 15 | [30 empty] | 15 | bar: DAY 1; DAY 3; DAY 5; DAY 7; DAY 9; DAY 11; DAY 13; DAY 15; DAY 17; DAY 19; DAY 22 to DAY 23; DAY 25 to DAY 27
Begin Corpus & Technical Manual | 50 | Alex | Complete | 50 | DAY 1: 5; DAY 2: 5; DAY 5: 5; DAY 6: 5; DAY 10: 5; DAY 14: 5; DAY 18: 5; DAY 20: 5; DAY 24: 5; DAY 30: 5 | 50
Sprint #5
Test Functions | 50 | Multiple Members | Complete | 50 | DAY 1: 5; DAY 3: 5; DAY 5: 5; DAY 7: 5; DAY 9: 5; DAY 11: 5; DAY 13: 5; DAY 15: 5; DAY 17: 5 | 50
Test Hardware | 50 | Jung-Mo | Complete | 50 | DAY 2: 5; DAY 4: 5; DAY 6: 5; DAY 8: 5; DAY 10: 5; DAY 12: 5; DAY 14: 5; DAY 16: 5; DAY 18: 5 | 50
Finalise Server Functionality | 50 | Multiple Members | Complete | 50 | DAY 2: 5; DAY 4: 5; DAY 6: 5; DAY 11: 5; DAY 14: 5; DAY 16: 5; DAY 21: 5; DAY 23: 5; DAY 27: 5; DAY 30: 5 | 50
Test Server | 50 | Multiple Members | Complete | 50 | DAY 1: 5; DAY 3: 5; DAY 11: 5; DAY 14: 5; DAY 16: 5; DAY 18: 5; DAY 19: 5; DAY 22: 5; DAY 24: 5; DAY 26: 5 | 50
Create Video | 30 | Multiple Members | Complete | 30 | DAY 1: 5; DAY 4: 5; DAY 7: 5; DAY 10: 5; DAY 13: 5; DAY 17: 5 | 30
Continue Corpus | 60 | Multiple Members | Complete | 60 | DAY 1: 5; DAY 3: 5; DAY 5: 5; DAY 7: 5; DAY 9: 5; DAY 11: 5; DAY 13: 5; DAY 15: 5; DAY 17: 5; DAY 19: 5; DAY 21: 5; DAY 23: 5 | 60
Continue Tech Report | 50 | Multiple Members | Complete | 50 | DAY 1: 5; DAY 3: 5; DAY 6: 5; DAY 8: 5; DAY 10: 5; DAY 20: 5; DAY 22: 5; DAY 25: 5; DAY 27: 5; DAY 29: 5 | 50
Sprint #6
Finish Corpus | 30 | Alex | Complete | 30 | DAY 1: 5; DAY 3: 5; DAY 5: 5; DAY 7: 5; DAY 9: 5; DAY 11: 5; DAY 13: 5; DAY 15: 5; DAY 17: 5; DAY 19: 5 | 30
Finish Tech Report | 30 | Alex | Complete | 30 | DAY 2: 5; DAY 4: 5; DAY 6: 5; DAY 8: 5; DAY 10: 5; DAY 12: 5 | 30
Finish Video | 15 | Walid | Complete | 15 | DAY 1: 5; DAY 9: 5; DAY 18: 5 | 15
Finish Testing | 40 | Igor | Complete | 40 | DAY 1: 5; DAY 5: 5; DAY 8: 5; DAY 10: 5; DAY 13: 5; DAY 16: 5; DAY 19: 5; DAY 21: 5 | 40
Start Individual Reports | 50 | Multiple Members | Complete | 50 | DAY 1: 5; DAY 3: 5; DAY 5: 5; DAY 7: 5; DAY 9: 5; DAY 11: 5; DAY 13: 5; DAY 15: 5; DAY 17: 5; DAY 19: 5 | 50
Upload Completed Work For Marking | 1 | Alex | Complete | 1 | [30 empty] | 1 | bar: DAY 30
TOTAL |  |  |  | 1314 | 110 | 63 | 79 | 67 | 77 | 63 | 74 | 60 | 73 | 62 | 65 | 37 | 63 | 42 | 53 | 37 | 48 | 37 | 48 | 27 | 33 | 19 | 14 | 17 | 13 | 8 | 13 | 7 | 12 | 18 | 1314

## Priority List
Priority List
Importance
Server Implementation | High
Java Socket Programming | High
PHP Scripting | Med
Hardware Sync | High
Registration Page PHP Script | Low
Circuit Building | High
Documentation | High
Android UI | Med
Android Functions | High
Data Mining | Low
API Implementation | Med
Voice Recognition | Med
Database Construction | High
Security Measures | Med
QA Testing | Med
Video | Med
Tech Report | High
Indavidual Reports | Med
System Sync | High
Hardware Acquisition | High
Hardware Research | High